## Summary
Bug report
| iOS-Bug Report | [8 empty] | Categories Wise-iOS Bug Report
| Device Name | Cluster Name | APK Version | Total Bugs | Active | Closed | In-Progress | NA | Blocked | APK Version | Total Bugs | Active | Closed | In-Progress | NA | Blocked
| IOS | U490 | 4.2.1 (5) | 26 | 26 | 0 | 0 | 0 | 0 | Connectivity | 4 | 0 | 2 | 0 | 0 | 2
| IOS | U490 | 4.2.1 (7) | 26 | 20 | 6 | 0 | 0 | 0 | App Crash | 3 | 0 | 3 | 0 | 0 | 0
| IOS | U490 | 4.2.1 (10) | 26 | 19 | 7 | 0 | 0 | 0 | Navigation | 2 | 1 | 0 | 1 | 0 | 0
| IOS | U490 | 4.2.1 (14) | 26 | 19 | 7 | 0 | 0 | 0 | Cluster Issue | 8 | 1 | 2 | 0 | 0 | 5
| IOS | U490 | 4.2.1 (15) | 26 | 19 | 7 | 0 | 0 | 0 | VA | 4 | 3 | 1 | 0 | 0 | 0
| IOS | U490 | 4.2.1 (22) | 28 | 21 | 7 | 0 | 0 | 0 | UI Issue | 1 | 0 | 1 | 0 | 0 | 0
| IOS | U490 | 4.2.1 (27) | 33 | 25 | 8 | 0 | 0 | 0 | MAP | 16 | 7 | 5 | 0 | 0 | 4
| IOS | U490 | 4.4.0 (15) | 39 | 14 | 19 | 1 | 0 | 5 | Others | 21 | 4 | 10 | 0 | 0 | 7
| IOS | U490 | 4.4.0 (18) | 39 | 14 | 19 | 1 | 0 | 5 | Total : | 59 | 16 | 24 | 1 | 0 | 18
| IOS | U490 | 4.4.0 (24) | 45 | 14 | 20 | 1 | 0 | 10
| IOS | U490 | 4.4.0 (37) | 51 | 8 | 24 | 1 | 0 | 18
| IOS | U490 | 4.4.1 (13) | 53 | 10 | 24 | 1 | 0 | 18
| IOS | U490 | 4.5.1 (3) | 59 | 16 | 24 | 1 | 0 | 18
Latest build
| Android-Bug Report | [8 empty] | Categories Wise-Android Bug report
| Device Name | Cluster Name | APK Version | Total Bugs | Active | Closed | In-Progress | NA | Blocked | APK Version | Total Bugs | Active | Closed | In-Progress | NA | Blocked
| Android | U490 | 4.2.0.4901 | 16 | 8 | 8 | 0 | 0 | 0 | Connectivity | 11 | 0 | 7 | 1 | 0 | 3
| Android | U490 | 4.2.0.4902 | 18 | 7 | 11 | 0 | 0 | 0 | App Crash | 9 | 0 | 9 | 0 | 0 | 0
| Android | U490 | 4.2.0.4903 | 52 | 23 | 21 | 7 | 0 | 1 | Navigation | 3 | 0 | 3 | 0 | 0 | 0
| Android | U490 | 4.2.0.4904 | 61 | 10 | 35 | 3 | 0 | 13 | Cluster Issue | 16 | 0 | 4 | 0 | 0 | 12
| Android | U490 | 4.2.0.4905 | 69 | 18 | 37 | 2 | 0 | 12 | VA | 11 | 0 | 9 | 0 | 0 | 2
| Android | U490 | 4.2.0.4906 | 71 | 10 | 40 | 1 | 0 | 20 | UI Issue | 3 | 0 | 2 | 0 | 0 | 1
| Android | U490 | 4.3.1.4907 | 73 | 13 | 39 | 1 | 0 | 20 | MAP | 5 | 0 | 5 | 0 | 0 | 0
| Android | U490 | 4.3.1.4908 | 80 | 5 | 55 | 1 | 0 | 19 | Others | 20 | 1 | 18 | 0 | 0 | 1
| Android | U490 | 4.4.0.4911 | 78 | 3 | 55 | 1 | 0 | 19 | Total : | 78 | 1 | 57 | 1 | 0 | 19
| Android | U490 | 4.5.0.4909 | 78 | 1 | 57 | 1 | 0 | 19
Latest build
Active Test cases |  |  | Active
Failed Test Cases |  |  | Fail
Passed Test cases |  |  | Pass
NA Test Cases |  |  | NA
| App link | App Center

## Android Bugs
Sl. No. | Bug Id | Categories | Bug description | Build Version | Priority | Device info | Platform | Status(4.2.0.4901) | Status(4.2.0.4902) | Status(4.2.0.4903(U490)) | Status(4.2.0.4904(U490)) | Status(4.2.0.4905(U490)) | Status(4.2.0.4906(U490)) | Status(4.3.1.4907(U490)) | Status(4.3.1.4908(U490)) | Status(4.4.0.4911(U490)) | Status(4.5.0.4909(U490)) | QA Observation | Comments | Pricol Team
1 | DOM-183 | Connectivity | [Android]DND state auto rejection is not working. | 4.2.0.4901/4.2.0.4902 | P2 | Model: Motorola Edge 30 Android version: 13 | Android | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed
2 | DOM-181 | Connectivity | [IOS]TVS connect app premium app is not Opening | 4.2.0.4901/4.2.0.4902 | P1 | Model: Motorola Edge 30 Android version: 13 | IOS | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed
3 | DOM-182 | App Crash | [Android]App is crashing when user receives an incoming call. | 4.2.0.4901/4.2.0.4902 | P0 | Model: Motorola Edge 30 Android version: 13 | Android | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed
4 | DOM-184 | Others | [Android]Back fuctionality is not working when the toggle button is enabled. | 4.2.0.4901/4.2.0.4902 | P3 | Model: Motorola Edge 30 Android version: 13 | Android | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed
5 | DOM-185 | UI Issue | [IOS]After pairing the device with cluster, UI is wrongly displayed and not able to switch to another page. | 4.2.0.4901/4.2.0.4902 | P1 | Model: Motorola Edge 30 Android version: 13 | IOS/Android | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed
6 | DOM-189 | Connectivity | [Android]The cluster gets disconnected when there is an incoming call in the DND state. | 4.2.0.4901/4.2.0.4902 | P3 | Model: Motorola Edge 30 Android version: 13 | Android | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed
7 | DOM-190 | Others | [Android]User Manual not displayed | 4.2.0.4901/4.2.0.4902 | P2 | Model: Motorola Edge 30 Android version: 13 | Android | Active | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed
8 | DOM-191 | Others | [Android]Profile picture is displayed blank for a while when we upload the image by zooming. | 4.2.0.4901/4.2.0.4902 | P3 | Model: Motorola Edge 30 Android version: 13 | Android | Active | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed
9 | DOM-192 | Cluster Issue | [Android]MAP Simulation is not happening. | 4.2.0.4901/4.2.0.4902 | P2 | Model: Motorola Edge 30 Android version: 13 | Android | Active | Active | Active | Blocked | Blocked | Blocked | Blocked | Closed | Closed | Closed | Simulation is not part u399 cluster(Above os 12 not working LoKITO)Vehicle level testing required
10 | DOM-193 | MAP | [Android]The Black box is displayed on the MAP while navigating. | 4.2.0.4901/4.2.0.4902 | P3 | Model: Motorola Edge 30 Android version: 13 | Android | Closed | Closed | Closed | In Progress | Active | Active | Active | Closed | Closed | Closed | Next Build | Implemented released in next build
11 | DOM-194 | Others | [Android][IOS]A Valid Bike image is not displayed on the home screen. | 4.2.0.4901/4.2.0.4902 | P3 | Model: Motorola Edge 30 Android version: 13 | Android and IOS | Active | Active | Blocked | Blocked | Blocked | Blocked | Blocked | Blocked | Blocked | Blocked |  | Yet to get the images from Marketing |  | Android and iOS
12 | DOM-196 | MAP | [Android]The "Current location not available" message is displayed when location we start navigating. | 4.2.0.4901/4.2.0.4902 | P2 | Model: Motorola Edge 30 Android version: 13 | Android | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed
13 | DOM-198 | Cluster Issue | [Android]If the incoming call is received/Disconnected from mobile then the "Calling "text is displayed in the cluster. | 4.2.0.4901/4.2.0.4902 | P2 | Model: Motorola Edge 30 Android version: 13 | Android | Active | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed
14 | DOM-223 | MAP | App crash is observed after clicking the Get location functionality. | 4.2.0.4901/4.2.0.4902 | P1 | Model: Motorola Edge 30 Android version: 13 | Android | Active | Active | In Progress | Closed | Closed | Closed | Closed | Closed | Closed | Closed
15 | DOM-224 | Others | Profile first name and Last name accepting Digits | 4.2.0.4901/4.2.0.4902 | P1 | Model: Motorola Edge 30 Android version: 13 | Android | Active | Active | Active | Closed | Closed | Closed | Closed | Closed | Closed | Closed
16 | DOM-236 | Cluster Issue | [Android]After receiving/Disconnecting the call, In the cluster time duration not displayed. | 4.2.0.4901/4.2.0.4902 | P2 | Model: Motorola Edge 30 Android version: 13 | Android | Active | Active | In Progress | Closed | Closed | Closed | Closed | Closed | Closed | Closed | There is no such requirement in U399
17 | DOM-243 | App Crash | [Android] App crash observed when we are in navigation page. | 4.2.0.4901/4.2.0.4902 | P0 | Model: Motorola Edge 30 Android version: 13 | Android |  | Active | In Progress | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Keep it for observation 1 Week
18 | DOM-244 | MAP | Multiple times Edit, Zoom In and Zoom out Map is blinking. | 4.2.0.4901/4.2.0.4902 | P1 | Model: Motorola Edge 30 Android version: 13 | Android |  | Active | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed
19 | DOM-246 | Others | Edit profile page -While editing the first name and Last name ,Space fuctionality is not working properly. Instead deleting the characters. | 4.2.0.4903 | P1 | Model: Motorola Edge 30 Android version: 13 | Android |  |  | Active | Closed | Closed | Closed | Closed | Closed | Closed | Closed
20 | DOM-248 | Others | The "About Us" option is displayed as "About" in the left selection view. | 4.2.0.4903 | P2 | Model: Motorola Edge 30 Android version: 13 | Android |  |  | Active | Closed | Closed | Closed | Closed | Closed | Closed | Closed
21 | DOM-249 | Others | Duplicate bikes are displayed in the vehicle garage. | 4.2.0.4903 | P1 | Model: Motorola Edge 30 Android version: 13 | Android |  |  | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed
22 | DOM-247 | Others | Emergency contact details did not accept the Space in the first name and Last name field. | 4.2.0.4903 | P2 | Model: Motorola Edge 30 Android version: 13 | Android |  |  | Active | Closed | Closed | Closed | Closed | Closed | Closed | Closed
23 | DOM-252 | Connectivity | Profile picture is taking log time to upload. | 4.2.0.4903 | P2 | Model: Motorola Edge 30 Android version: 13 | Android |  |  | In Progress | In Progress | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | This is improvement point | This is common for all the bikes and working as per live behaviour. Need to re-write the logic to improve the time. Will talk to CX team about which team to handle.
24 | DOM-253 | Others | While updating Profile details ask for Email id. | 4.2.0.4903 | P2 | Model: Motorola Edge 30 Android version: 13 | Android |  |  | Active | Closed | Closed | Closed | Closed | Closed | Closed | Closed
25 | DOM-250 | App Crash | The App is crashing when we are on the Vehicle garage page. | 4.2.0.4903 | P0 | Model: Motorola Edge 30 Android version: 13 | Android |  |  | Active | Closed | Closed | Closed | Closed | Closed | Closed | Closed
26 | DOM-251 | App Crash | The App is crashing when we are on the locate page. | 4.2.0.4903/4.2.0.4904 | P0 | Model: Motorola Edge 30 Android version: 13 | Android |  |  | In Progress | Closed | Closed | Closed | Closed | Closed | Closed | Closed
27 | DOM-254 | Others | While adding the vehicle accepting mobile numbers in the place of Engine numbers. | 4.2.0.4903 | P1 | Model: Motorola Edge 30 Android version: 13 | Android |  |  | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed |  |  |  | Android and iOS
28 | DOM-255 | Others | The page redirects to the Home screen while deleting the Vehicle from the vehicle garage. | 4.2.0.4903 | P2 | Model: Motorola Edge 30 Android version: 13 | Android |  |  | Active | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Not a bug |  |  | Android
29 | DOM-256 | VA | Profile image not displayed in the cluster Through the voice command "Hi buddy" | 4.2.0.4903 | P2 | Model: Motorola Edge 30 Android version: 13 | Android |  |  | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed |  |  |  | Android and iOS
30 | DOM-259 | Navigation | The petrol pump, Hotels, and restaurant icons are overlapping the Road lines on the map navigation screen. | 4.2.0.4903 | P2 | Model: Motorola Edge 30 Android version: 13 | Android |  |  | Active | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Mappls Issue
31 | DOM-257 | VA | Duplicate items are displayed in the VA list. | 4.2.0.4903 | P2 | Model: Motorola Edge 30 Android version: 13 | Android |  |  | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed
32 | DOM-258 | Connectivity | After the end ride Bike image is not displayed. | 4.2.0.4903 | P1 | Model: Motorola Edge 30 Android version: 13 | Android |  |  | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed
33 | DOM-260 | MAP | In the application tapping on cluster image redirects to "about.mappls.com page" | 4.2.0.4903 | P1 | Model: Motorola Edge 30 Android version: 13 | Android |  |  | Active | Closed | Closed | Closed | Active | Closed | Closed | Closed | Mappls Issue
34 | DOM-261 | Cluster Issue | VA is not invoking in the cluster. | 4.2.0.4903 | P2 | Model: Motorola Edge 30 Android version: 13 | Android |  |  | Active | Active | Active | Blocked | Blocked | Blocked | Blocked | Blocked |  | Cluster side issue
35 | DOM-262 | VA | VA "end navigation "word is taken as and navigation | 4.2.0.4903 | P2 | Model: Motorola Edge 30 Android version: 13 | Android |  |  | Active | Closed | Closed | Closed | Closed | Closed | Closed | Closed | VA Fixed
36 | DOM-263 | VA | VA some times "Brightness dicrease" and "Brightness increase" options are not taking. | 4.2.0.4903 | P2 | Model: Motorola Edge 30 Android version: 13 | Android |  |  | Active | Active | Active | Closed | Closed | Closed | Closed | Closed | VA command not exist. | As per Requirement working fine
37 | DOM-264 | VA | List of Voice assist is not working. | 4.2.0.4903 | P1 | Model: Motorola Edge 30 Android version: 13 | Android |  |  | Active | Active | Active | Active | Active | Closed | Closed | Closed | As per the developer comment cosing the Bug. As designed | As designed bug
38 | DOM-265 | Connectivity | While login struck in the OTP screen. | 4.2.0.4903 | P1 | Model: Motorola Edge 30 Android version: 13 | Android |  |  | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed
39 | DOM-266 | Others | Over speed alert warning is displayed in every 30 second. | 4.2.0.4903 | P1 | Model: Motorola Edge 30 Android version: 13 | Android |  |  | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Not a bug
40 | DOM-267 | Others | Max deceleration is displayed as negative values. | 4.2.0.4903 | P1 | Model: Motorola Edge 30 Android version: 13 | Android |  |  | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Not a bug
41 | DOM-268 | Others | Not able to go back or cancel from over speeding page. | 4.2.0.4903 | P1 | Model: Motorola Edge 30 Android version: 13 | Android |  |  | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Not a bug
42 | DOM-269 | Connectivity | Taking Too much time to get connected with the cluster.. | 4.2.0.4903 | P1 | Model: Motorola Edge 30 Android version: 13 | Android |  |  | In Progress | Blocked | Blocked | Blocked | Blocked | Blocked | Blocked | Blocked | Cluster issue. | When we use the simulated cluster for more than 30 mins, then cluster should be restarted to connect again | R&D, Pricol, logs are attached
43 | DOM-270 | UI Issue | The Weather icon not displayed on the application. | 4.2.0.4903 | P2 | Model: Motorola Edge 30 Android version: 13 | Android |  |  | Active | Fixed | Active | Active | Active | Closed | Closed | Closed | Not fixed
44 | DOM-271 | UI Issue | Voice assist icon is displayed in red color | 4.2.0.4903/4.2.0.4904 | P2 | Model: Motorola Edge 30 Android version: 13 | Android |  |  | Active | Blocked | Blocked | Blocked | Blocked | Blocked | Blocked | Blocked | Need to be discussed with Graphics team | Asset replacement, Arshad to follow-up with UI/UX team to get the asset
45 | DOM-272 | Cluster Issue | Digi docs synchronization getting struck after receiving incoming call. | 4.2.0.4903/4.2.0.4904 | P2 | Model: Motorola Edge 30 Android version: 13 | Android |  |  | Active | Active | Active | Blocked | Blocked | Blocked | Blocked | Blocked |  | upload not synching
46 | DOM-273 | Connectivity | X20 and X10 smart connect not able to pair with the android mobile | 4.2.0.4903/4.2.0.4904 | P2 | Model: Motorola Edge 30 Android version: 13 | Android |  |  | Active | Active | Active | Blocked | Blocked | Blocked | Blocked | Blocked |  | X20 and X10 both are not discoverable ,Not able to connect
47 | DOM-279 | Cluster Issue | When we receive a missed call, In the cluster calling status is blinking. | 4.2.0.4903/4.2.0.4904 | P2 | Model: Motorola Edge 30 Android version: 13 | Android |  |  | Active | In Progress | In-Progress | Blocked | Blocked | Blocked | Blocked | Blocked |  | Arshad to attach the logs to make sure App is not sending the call info once the call is disconnected.
48 | DOM-291 | Cluster Issue | Digi doc upload not synching with the cluster | 4.2.0.4903/4.2.0.4904 | P1 | Model: Motorola Edge 30 Android version: 13 | Android |  |  | Active | Active | Active | Blocked | Blocked | Blocked | Blocked | Blocked |  | upload not synching
49 | DOM-284 | VA | For processing VA icon not displayed | 4.2.0.4903/4.2.0.4904 | P3 | Model: Motorola Edge 30 Android version: 13 | Android |  |  | Active | Blocked | Blocked | Blocked | Blocked | Blocked | Blocked | Blocked | Cluster issue need to be discussed | Deekshit to update the video/logs in Jira and Arshad to provide comments. Could be expected behaviour. | Issue reproduced
50 | DOM-285 | Cluster Issue | After pairing the cluster with an Android device, Not able to pair with the IOS device. | 4.2.0.4903/4.2.0.4904 | P1 | Model: Motorola Edge 30 Android version: 13 | Android |  |  | Active | Blocked | Blocked | Blocked | Blocked | Blocked | Blocked | Blocked | Cluster issue. | Deekshit to create the ticket and Prajwal to update the comment | R&D, Pricol
51 | DOM-280 | Cluster Issue | After decline the call fuel range is not displayed and the blank space is observed in the cluster. | 4.2.0.4903 | P2 | Model: Motorola Edge 30 Android version: 13 | Android |  |  | Active | Blocked | Blocked | Blocked | Blocked | Blocked | Blocked | Blocked | Cluster issue. | When we send the custom message, fuel range space is becoming blank | R&D, Pricol
52 | DOM-251 | App Crash | The App is crashing when we are on the locate page. | 4.2.0.4904 | P0 | Model: Motorola Edge 30 Android version: 13 | Android |  |  | In Progress | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Keep it for observation 1 Week
53 |  | Others | Rain mode is displayed even if there is no rain | 4.2.0.4904 | P2 | Model: Motorola Edge 30 Android version: 13 | Android |  |  |  | Active | Closed | Closed | Closed | Closed | Closed | Closed | Need to share the logs and video | Not reproducible, will be closed
54 | DOM-304 | Others | Over speed alert warning is displayed for 0 km/h | 4.2.0.4904 | P1 | Model: Motorola Edge 30 Android version: 13 | Android |  |  |  | Active | Closed | Active | Active | Closed | Closed | Closed
55 | DOM-281 | Connectivity | Text change - Error message for engine nunber validation is wrong | 4.2.0.4904 | P2 | Model: Motorola Edge 30 Android version: 13 | Android |  |  |  | Blocked | Active | Active | Active | Closed | Closed | Closed | Related to engine number login and Accepting mobile numbers
56 | DOM-286 | Cluster Issue | Unable to pair another device without forgetting the primary connected device. | 4.2.0.4904 | P1 | Model: Motorola Edge 30 Android version: 13 | Android |  |  |  | Blocked | Blocked | Blocked | Blocked | Blocked | Blocked | Blocked | Cluster level limitation |  |  | Manufacture Conneting sate Not establishing the connection with other mobile.
57 | DOM-287 | Cluster Issue | If ios and android device blutooth settings are enabled then not detect the Cluster. | 4.2.0.4904 | P1 | Model: Motorola Edge 30 Android version: 13 | Android |  |  |  | Blocked | Blocked | Blocked | Blocked | Blocked | Blocked | Blocked | Cluster level limitation |  |  | R&D, Pricol
58 | DOM-288 | Cluster Issue | Some times Pass code not displaying in the cluster. | 4.2.0.4904 | P1 | Model: Motorola Edge 30 Android version: 13 | Android |  |  |  | Blocked | Blocked | Blocked | Blocked | Blocked | Blocked | Blocked | Cluster level limitation |  |  | R&D, Pricol
59 | DOM-289 | Cluster Issue | On-going calls are displayed as “ Calling” in the cluster. | 4.2.0.4904 | P1 | Model: Motorola Edge 30 Android version: 13 | Android |  |  |  | Blocked | Blocked | Blocked | Blocked | Blocked | Blocked | Blocked | To be discussed | Arshad to attach the logs where App is sending the correct call status. | This cluster Status won't be displayed | Arshad
60 | DOM-290 | Cluster Issue | Unknown number caller "calling "status not displayed in the cluster. | 4.2.0.4904 | P1 | Model: Motorola Edge 30 Android version: 13 | Android |  |  |  | Blocked | Blocked | Blocked | Blocked | Blocked | Blocked | Blocked | Cluster level limitation | Cluster has 2 rows where it displays 'unknown number' text in first row and the actual number in second row so no space for displaying 'calling status' | Need to discuss with TVS Team | R&D, Pricol
61 | DOM-283 | Connectivity | The next day Unpaired State asked for the end ride | 4.2.0.4904 | P1 | Model: Motorola Edge 30 Android version: 13 | Android |  |  |  | Active | Active | Active | Active | Closed | Closed | Closed
62 | DOM-292 | Cluster Issue | Need to restart the cluster once we are used to it testing continuously for 30 mins. | 4.2.0.4905 | P1 | Model: Motorola Edge 30 Android version: 13 | Android |  |  |  | Active | Active | Blocked | Blocked | Blocked | Blocked | Blocked
63 | DOM-293 | App Crash | The app crashes when the user tries to view the vehicle settings. | 4.2.0.4905 | P0 | Model: Motorola Edge 30 Android version: 13 | Android |  |  |  |  | Active | Closed | Closed | Closed | Closed | Closed
64 | DOM-294 | App Crash | The Black screen is observed when the user tries to view the settings in paired state. | 4.2.0.4905 | P0 | Model: Motorola Edge 30 Android version: 13 | Android |  |  |  |  | Active | Closed | Closed | Closed | Closed | Closed
65 | DOM-295 | Navigation | Re-center button functionality is not working while navigating. | 4.2.0.4905 | P1 | Model: Motorola Edge 30 Android version: 13 | Android |  |  |  |  | Active | Closed | Closed | Closed | Closed | Closed
66 | DOM-296 | Others | Getting black screen in the profile section | 4.2.0.4906 | P1 | Model: Motorola Edge 30 Android version: 13 | Android |  |  |  |  | Active | Active | Active | Closed | Closed | Closed
67 | DOM-300 | Connectivity | After forgetting the device manually from the cluster, Application still is in connected state. | 4.2.0.4906 | P1 | Model: Motorola Edge 30 Android version: 13 | Android |  |  |  |  | Active | Blocked | Blocked | Blocked | Blocked | Blocked |  | Implementation is in discussion.
68 | DOM-303 | VA | VA command navigating to an anonymous places. | 4.2.0.4906 | P1 | Model: Motorola Edge 30 Android version: 13 | Android |  |  |  |  | Active | Active | Active | Closed | Closed | Closed
69 | DOM-305 | Navigation | After clicking Navigate, the Find My Vehicle location is displayed wrongly. | 4.2.0.4906 | P1 | Model: Motorola Edge 30 Android version: 13 | Android |  |  |  |  | Active | Active | Active | Closed | Closed | Closed |  | Repro in latest build-4.3.1.4908(U490)
70 | DOM-306 | Cluster Issue | [Digi Docs]It is not possible to Delete the existing documents from the cluster. | 4.2.0.4906 | P0 | Model: Motorola Edge 30 Android version: 13 | Android | [5 empty] | Blocked | Blocked | Blocked | Blocked | Closed | 1. Deletion able to perform from Cluster. 2.Deletion pop up message not displayed on the cluster After deletion. 3. Cluster level able to delete but Application not deleting the image. |  |  |  | Closed
71 | DOM-309 | VA | The Voice Assist Option is not present in the Left slider menu. | 4.2.0.4906 | P0 | Model: Motorola Edge 30 Android version: 13 | Android | [5 empty] | Active | Active | Closed | Closed | Closed
72 | DOM-328 | App Crash | The app crashed on the Last ride info page. | 4.3.1.4907 | P0 | Model: Motorola Edge 30 Android version: 13 | Android | [6 empty] | Active | Closed | Closed | Closed
73 | DOM-329 | App Crash | The app is closed on tapping on the terms and conditions option. | 4.3.1.4907 | P0 | Model: Motorola Edge 30 Android version: 13 | Android | [6 empty] | Active | Closed | Closed | Closed
74 | DOM-331 | Others | While adding emergency contacts,If I press two times Space key then dot is displayed. | 4.3.1.4908 | P2 | Model: Motorola Edge 30 Android version: 13 | Android | [7 empty] | Closed | Closed | Closed
75 | DOM-330 | VA | “Hi Buddy” Voice command not accepting in the cluster. | 4.3.1.4908 | P2 | Model: Motorola Edge 30 Android version: 13 | Android | [7 empty] | Active | Active | Closed
76 | DOM-340 | VA | If the VA is invoked when cluster is in the Sport mode then "calling" text is displayed. on the cluster instead “Listening”. | 4.3.1.4908 | P1 | Model: Motorola Edge 30 Android version: 13 | Android | [7 empty] | Active | Active | Blocked
77 | DOM-341 | VA | Track Mode-VA option/Icon is not visible on the Application. | 4.3.1.4908 | P1 | Model: Motorola Edge 30 Android version: 13 | Android | [7 empty] | Closed | Closed | Closed |  | As designed
78 | DOM-342 | Others | After uploading the profile picture blank screen is displayed. | 4.4.0.4911 | P1 | Model: Motorola Edge 30 Android version: 13 | Android | [8 empty] | Active | Active
79 | DOM-352 | Others | [Android][Digi Docs]On clicking on SYNC LOCKER TO VEHICLE App crash is observed. | 4.3.1.4908 | P0 | Model: Motorola Edge 30 Android version: 13 | Android | [7 empty] | Active
80 | DOM-353 | Navigation | [Android][U490]VA is Not invoking in the MAP/Navigation screen. | 4.3.1.4908 | P1 | Model: Motorola Edge 30 Android version: 13 | Android | [7 empty] | Active
81 | DOM-355 | Navigation | [Android][U490]VA is Not invoking in the MAP/Navigation screen. | 4.3.1.4908 | P1 | Model: Motorola Edge 30 Android version: 13 | Android | [7 empty] | Active
Active
Closed
In Progress
NA
Blocked

## IOS Bugs
Sl. No. | Jira Bug Id | Categories | Bug description | Test steps | Build Version | Priority | Device info | Platform | Status(4.2.1(5)) | Status(4.2.1(7)) | Status(4.2.1(10)) | Status(4.2.1(14)) | Status(4.2.1(15)) | Status(4.2.1(22)) | Status(4.2.1(27)) | Status(4.4.0(15)) | Status(4.4.0(18)) | Status(4.4.0(24)) | Status(4.4.0(37)) | Status(4.4.1(13)) | Status(4.4.1(13)) | Dev-status | Comments
1 | https://tvsmotorcompany.atlassian.net/browse/DOM-195 | Connectivity | Emergency SOS is not working and The call is not going to the emergency number. | 1. Installed the build 2. Log in with valid credential 3. Go to the home page 4. Connect with the cluster 5. Go to the live Dashboard 6. Click on side Menu 7. Tap on Emergency SOS | 4.2.1 (5) | P2 | Model Name: Iphone 13 IOS Version: 16.4.1 | IOS | Active | Active | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Blocked | SOS Sent only message to emergency contact :like:: "Hi, this is . I need an urgent help. Please tap here maps.google.com/?q=30.340000,78.040000 to check my current location. You have received the message because your mobile no is listed as an emergency contact in TVS Connect app."
2 | https://tvsmotorcompany.atlassian.net/browse/DOM-197 | Connectivity | The Cluster Connection not happening. | 1. Installed the build 2. Log in with valid credential 3. Go to the home page 4. Connect with the cluster | 4.2.1 (5) | P1 | Model Name: Iphone 13 IOS Version: 16.4.1 | IOS | Active | Active | Active | Active | Active | Active | Active | Active | Active | Blocked | Blocked | Blocked | Blocked | Blocked | Not an issue(At that movement cluster issue)
3 | https://tvsmotorcompany.atlassian.net/browse/DOM-203 | App Crash | Map is through error. | 1. Installed the build 2. Log in with valid credential 3. Go to the home page 4. Connect with the cluster 5. Go to the live Dashboard 6. Search a destination | 4.2.1 (5) | P1 | Model Name: Iphone 13 IOS Version: 16.4.1 | IOS | Active | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Done | Closed
4 | https://tvsmotorcompany.atlassian.net/browse/DOM-200 | Others | In Cluster displayed "calling" status instead of ongoing or disconnected. | 1. Installed the build 2. Log in with valid credential 3. Go to the home page 4. Connect with the cluster 5.Go to the live Dashboard 6. Give a call to the register no. | 4.2.1 (5) | P1 | Model Name: Iphone 13 IOS Version: 16.4.1 | IOS | Active | Active | Active | Active | Active | Active | Active | Active | Active | Blocked | Blocked | Blocked | Blocked | In review | Open
5 | https://tvsmotorcompany.atlassian.net/browse/DOM-199 | UI Issue | App Response is very Slow | 1. Installed the build 2. Log in with valid credential 3. Go to the home page 4. Click on profile section | 4.2.1 (5) | P1 | Model Name: Iphone 13 IOS Version: 16.4.1 | IOS | Active | Active | Active | Active | Active | Active | Active | Closed | Closed | Closed | Closed | Closed | Closed | In progress | This will take time Need to improved app resposiveness Please do one more round of testing and let us know from which screen responsiveness decreses
6 | https://tvsmotorcompany.atlassian.net/browse/DOM-208 | Connectivity | Emergency Contact accept Invalid Mail ID | 1. Installed the build 2. Log in with valid credential 3. Go to the home page 4. Click on profile section 5. Click on profile 6. Go to Emergency Contact | 4.2.1 (5) | P2 | Model Name: Iphone 13 IOS Version: 16.4.1 | IOS | Active | Active | Active | Active | Active | Active | Active | Closed | Closed | Closed | Closed | Closed | Closed |  |  | Android and iOS
7 | https://tvsmotorcompany.atlassian.net/browse/DOM-209 | Others | Non-Cropable profile Photo | 1. Installed the build 2. Log in with valid credential 3. Go to the home page 4. Click on profile section | 4.2.1 (5) | P3 | Model Name: Iphone 13 IOS Version: 16.4.1 | IOS | Active | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Done
8 | https://tvsmotorcompany.atlassian.net/browse/DOM-210 | Others | Not editable Profile section | 1. Installed The build 2. Log in with valid credential 3. Go to the home page 4. Click on profile section 5. Click on profile | 4.2.1 (5) | P2 | Model Name: Iphone 13 IOS Version: 16.4.1 | IOS | Active | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Done
9 | https://tvsmotorcompany.atlassian.net/browse/DOM-204 | Cluster Issue | Feedback section not accepting mandatory field. | 1. Installed the build 2. Log in with valid credential 3. Go to the home page 4. Click on profile section 5. Click on Feedback | 4.2.1 (5) | P2 | Model Name: Iphone 13 IOS Version: 16.4.1 | IOS | Active | Active | Active | Active | Active | Active | Active | Blocked | Blocked | Blocked | Blocked | Blocked | Blocked | Blocked | Need to discuss Exisiting behaviour | Android and iOS
10 | https://tvsmotorcompany.atlassian.net/browse/DOM-211 | MAP | Profile pic taking time to upload. | 1. Installed the build 2. Log in with valid credential 3. Go to the home page 4. Click on profile section 5. Click on profile | 4.2.1 (5) | P2 | Model Name: Iphone 13 IOS Version: 16.4.1 | IOS | Active | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Done
11 | https://tvsmotorcompany.atlassian.net/browse/DOM-202 | Others | Digi Docs not able to synchronised. | 1. Installed The build 2. Log in with valid credential 3. Go to the home page 4. Click on profile section 5. Click on Digi Docs | 4.2.1 (5) | P2 | Model Name: Iphone 13 IOS Version: 16.4.1 | IOS | Active | Active | Active | Active | Active | Active | Active | Blocked | Blocked | Blocked | Blocked | Blocked | Blocked | In review | Cluster issue Already sent a mail to Herani
12 | https://tvsmotorcompany.atlassian.net/browse/DOM-205 | MAP | Last park location | 1. Installed The build 2. Log in with valid credential 3. Go to the home page 4. Click on last park location | 4.2.1 (5) | P1 | Model Name: Iphone 13 IOS Version: 16.4.1 | IOS | Active | Active | Active | Active | Active | Active | Active | Closed | Closed | Closed | Closed | Closed | Closed
13 | https://tvsmotorcompany.atlassian.net/browse/DOM-201 | Cluster Issue | Last Park location Fluctation | 1. Installed The build 2. Log in with valid credential 3. Go to the home page 4. Click on last park location | 4.2.1 (5) | P2 | Model Name: Iphone 13 IOS Version: 16.4.1 | IOS | Active | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Done
14 | https://tvsmotorcompany.atlassian.net/browse/DOM-207 | MAP | Shop Option is asking Registered person details | 1. Installed The build 2. Log in with valid credential 3. Go to the home page 4. Click on Shop | 4.2.1 (5) | P2 | Model Name: Iphone 13 IOS Version: 16.4.1 | IOS | Active | Active | Active | Active | Active | Active | Active | Active | Active | Blocked | Blocked | Blocked | Blocked | Blocked | Not an issue expecting to redirect to the SOP screen. | Android and iOS
15 | https://tvsmotorcompany.atlassian.net/browse/DOM-206 | Others | User Manual is Not displayed | 1. Installed The build 2. Log in with valid credential 3. Go to the home page 4. Click on profile section 5. tap on User Manual 5. Click on Know Your Bike 6. Go to User Manual | 4.2.1 (5) | P3 | Model Name: Iphone 13 IOS Version: 16.4.1 | IOS | Active | Active | Active | Active | Active | Active | Closed | Closed | Closed | Closed | Closed | Closed | Closed
16 | https://tvsmotorcompany.atlassian.net/browse/DOM-212 | Cluster Issue | Feedback mail is not coming to the respective mail id | 1. Installed the build 2. Log in with valid credential 3. Go to the home page 4. Click on profile section 5. Click on Feedback | 4.2.1 (5) | P2 | Model Name: Iphone 13 IOS Version: 16.4.1 | IOS | Active | Active | Active | Active | Active | Active | Active | Closed | Closed | Closed | Closed | Closed | Closed
17 | https://tvsmotorcompany.atlassian.net/browse/DOM-216 | App Crash | Not able to edit the emergency contact. | 1. Installed The build 2. Log in with valid credential 3. Go to the home page 4. Click on profile section 5. Click on profile 6. Go to Emergency Contact | 4.2.1 (5) | P2 | Model Name: Iphone 13 IOS Version: 16.4.1 | IOS | Active | Active | Active | Active | Active | Active | Active | Closed | Closed | Closed | Closed | Closed | Closed
18 | https://tvsmotorcompany.atlassian.net/browse/DOM-215 | MAP | Vehicle info accepting special character in vehicle info page. | 1.Installed The build 2. Log in with valid credential 3. Go to the home page 4.Click on profile section 5. Click on vehicle setting. 6. Go to Vehicle information 7. Enter the vehicle details | 4.2.1 (5) | P3 | Model Name: Iphone 13 IOS Version: 16.4.1 | IOS | Active | Active | Active | Active | Active | Active | Active | Closed | Closed | Closed | Closed | Closed | Closed |  | Closed
19 | https://tvsmotorcompany.atlassian.net/browse/DOM-214 | Others | Warranty is same for all bike. | 1. Installed The build 2. Log in with valid credential 3. Go to the home page 4. Click on profile section 5. tap on User Manual 5. Click on Know Your Bike 6. Go to Warranty | 4.2.1 (5) | P2 | Model Name: Iphone 13 IOS Version: 16.4.1 | IOS | Active | Active | Active | Active | Active | Active | Active | Closed | Closed | Closed | Closed | Closed | Closed | Blocked | Once we get the details we will update | Android and iOS
20 | https://tvsmotorcompany.atlassian.net/browse/DOM-213 | Others | Forgot Bluetooth message is receive in application. | 1. Installed The build 2. Log in with valid credential 3. Go to the home page | 4.2.1 (5) | P1 | Model Name: Iphone 13 IOS Version: 16.4.1 | IOS | Active | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed | Closed
21 | https://tvsmotorcompany.atlassian.net/browse/DOM-222 | Others | Application get hanged | 1. Installed the build 2. Log in with valid credential 3. Go to the home page 4. Click on profile section 5. Click on profile | 4.2.1 (10) | P1 | Model Name: Iphone 13 IOS Version: 16.4.1 | IOS | Active | Active | Active | Active | Active | Active | Active | Closed | Closed | Closed | Closed | Closed | Closed
22 | https://tvsmotorcompany.atlassian.net/browse/DOM-221 | Others | The Emergency SOS is sending SMS instead of call. | 1. Installed the build 2. Log in with valid credential 3. Go to the home page 4. Connect with the cluster 5. Go to the live Dashboard 6. Click on side Menu 7. Tap on Emergency SOS | 4.2.1 (10) | P1 | Model Name: Iphone 13 IOS Version: 16.4.1 | IOS | Active | Active | Active | Active | Active | Active | Active | Closed | Closed | Closed | Closed | Closed | Closed | Close | Currently sending SMS | Android and iOS
23 | https://tvsmotorcompany.atlassian.net/browse/DOM-220 | Connectivity | For Unknown number, "calling" status is not showing in the cluster. | 1. Installed the build 2. Log in with valid credential 3. Go to the home page 4. Connect with the cluster 5.Go to the live Dashboard 6. Give a call to the register no. | 4.2.1 (10) | P2 | Model Name: Iphone 13 IOS Version: 16.4.1 | IOS | Active | Active | Active | Active | Active | Active | Active | Active | Active | Blocked | Blocked | Blocked | Blocked | Blocked | Active
24 | https://tvsmotorcompany.atlassian.net/browse/DOM-218 | Others | The Service center POI didn't showing the distance details. | 1. Installed the build 2. Log in with valid credential 3. Go to the home page 4. Connect with the cluster 5. Go to the live Dashboard 6. Tap on Search 7. Click on Service Center from POI option | 4.2.1 (10) | P1 | Model Name: Iphone 13 IOS Version: 16.4.1 | IOS | Active | Active | Active | Active | Active | Active | Active | Active | Active | Blocked | Blocked | Blocked | Blocked | Blocked | Exisiting behaviour | Android and iOS
25 | https://tvsmotorcompany.atlassian.net/browse/DOM-217 | Cluster Issue | Device connection is not happening in the cluster. | 1. Installed the build 2. Log in with valid credential 3. Go to the home page 4. Connect with the cluster | 4.2.1 (10) | P1 | Model Name: Iphone 13 IOS Version: 16.4.1 | IOS | Active | Active | Active | Active | Active | Active | Active | Blocked | Blocked | Blocked | Blocked | Blocked | Blocked | Blocked | Cluster issue Already sent a mail to Herani
26 | https://tvsmotorcompany.atlassian.net/browse/DOM-219 | App Crash | Map got Completely blank in Last park location. | 1. Installed The build 2. Log in with valid credential 3. Go to the home page 4. Click on last park location | 4.2.1 (10) | P1 | Model Name: Iphone 13 IOS Version: 16.4.1 | IOS | Active | Active | Active | Active | Active | Active | Active | Closed | Closed | Closed | Closed | Closed | Closed | In review | Done
27 | DOM-297 | Cluster Issue | Not able to connect with the cluster. | Installed The build Log in with valid credential Go to the home page Try to pair with the cluster with click in connect option. | 4.2.1 (27) | P1 | Model Name: Iphone 13 IOS Version: 16.4.1 | IOS | [5 empty] | Active | Active | Blocked | Blocked | Blocked | Blocked | Blocked | Blocked
28 | DOM-298 | Others | Speed Alert is not working properly and a warning message keeps on displaying on the screen. | Installed the build Log in with valid credential Go to the home page Connect with the cluster. Simulate the cluster more then speed limit. | 4.2.1 (27) | P1 | Model Name: Iphone 13 pro Max IOS Version: 17.4 | IOS | [5 empty] | Active | Active | Active | Active | Closed | Closed | Closed | Closed
29 | DOM-299 | Cluster Issue | The application TPMS value is different from cluster. | 1. Installed The build 2. Log in with valid credential 3. Go to the home page 4. Try to pair with the cluster with click in connect option. 5. Observe the TPMS warning troughing in the phone. | 4.2.1 (27) | P0 | Model Name: iPhone 13 pro max IOS Version: 17.4 | IOS | [6 empty] | Active | Blocked | Blocked | Blocked | Blocked | Blocked | Blocked
30 | DOM-301 | Navigation | VA is not working | 1. Installed The build 2. Log in with valid credential 3. Go to the home page 4. Try to pair with the cluster with click in connect option. 5. Click on mike option, Give the command from VA list. | 4.2.1 (27) | P0 | Model Name: iPhone 13 pro max IOS Version: 17.4 | IOS | [6 empty] | Active | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress
31 | DOM-302 | VA | Cluster Km is not synchronized with the cluster. | 1. Installed The build 2. Log in with valid credential 3. Go to the home page 4. Try to pair with the cluster with click in connect option. | 4.2.1 (27) | P0 | Model Name: iPhone 13 pro max IOS Version: 17.4 | IOS | [6 empty] | Active | Closed | Closed | Closed | Closed | Closed | Closed
32 | DOM-307 | Others | POI option is not able to select. | 1. Installed the Build 2. Log in with valid Credential 3.Go to the Home Page 4.Click on Connect 5.Click on map in live Dashboard. 6.Click on Search 7.Tap on POI | 4.4.0 (15) | P1 | Model Name: iPhone 13 pro max IOS Version: 17.4 | IOS | [6 empty] | Active | Active | Active | Active | Closed | Closed | Closed
33 | DOM-308 | Cluster Issue | In the Cluster Continuously connection and disconnection is happening while in MAP page. | 1.Installed the build 2.Log in with valid credential 3.Go to the home page 4.Clicked on connect 5.Clicked on map in live dashboard. 6.Clicked on search 7.Tap on POI/ Search a destination | 4.4.0 (15) | P0 | Model Name: iPhone 13 pro max IOS Version: 17.4 | IOS | [6 empty] | Active | Active | Active | Active | Blocked | Blocked | Blocked
34 | DOM-310 | MAP | Last ride infromation having extra current location. |  | 4.4.0 (15) | P0 | Model Name: iPhone 13 pro max IOS Version: 17.4 | IOS | [7 empty] | Active | Active | Active | Closed | Closed | Closed
35 | DOM-222 | Others | App got hanged |  | 4.4.0 (15) | P0 | Model Name: iPhone 13 pro max IOS Version: 16.4 | IOS | [7 empty] | Active | Active | Active | Closed | Closed | Closed |  | IOS Version:17.4 not reproduced
36 | DOM-311 | Others | Multiple spaces accepting in profile section. |  | 4.4.0 (15) | P0 | Model Name: iPhone 13 pro max IOS Version: 17.4 | IOS | [7 empty] | Active | Active | Active | Blocked | Blocked | Blocked |  | 16.4 also reproceble | iOS
37 | DOM-314 | MAP | In Last Ride Information page the map path is not forming ideal path. |  | 4.4.0 (15) | P0 | Model Name: iPhone 13 pro max IOS Version: 17.4 | IOS | [7 empty] | Active | Active | Active | Blocked | Blocked | Blocked |  | 16.4 also reproceble | iOS
38 | DOM-313 | MAP | Recentre is not woring |  | 4.4.0 (15) | P0 | Model Name: iPhone 13 pro max IOS Version: 17.4 | IOS | [7 empty] | Active | Active | Active | Active | Active | Active |  | 16.4 also reproceble | iOS
39 | DOM-312 | MAP | Direcction of the Navigation icon is wrongly shown in the map. |  | 4.4.0 (15) | P0 | Model Name: iPhone 13 pro max IOS Version: 17.4 | IOS | [7 empty] | Active | Active | Active | Blocked | Blocked | Blocked |  | Bike level testing required | iOS
40 | DOM-319 | MAP | Some unwanted image is displayed in the corner of map screen. |  | 4.4.0(24) | P1 | Model Name: iPhone 13 pro max IOS Version: 17.4 | IOS | [9 empty] | Active | Closed | Closed | Closed
41 | DOM-320 | Navigation | The Distance & Navigation details are not displaying in the application as well as in the cluster. |  | 4.4.0(24) | P1 | Model Name: iPhone 13 pro max IOS Version: 17.4 | IOS | [9 empty] | Active | Active | Active | Active
42 | DOM-321 | Others | Not able to book a Vehicle service. |  | 4.4.0(24) | P1 | Model Name: iPhone 13 pro max IOS Version: 17.4 | IOS | [9 empty] | Active | Blocked | Blocked | Blocked |  |  | Android and iOS
43 | DOM-322 | MAP | In AOG page map is not displaying. |  | 4.4.0(24) | P1 | Model Name: iPhone 13 pro max IOS Version: 17.4 | IOS | [9 empty] | Active | Blocked | Blocked | Blocked |  |  | iOS
44 | DOM-323 | Others | Feedback section able to submit without mandatory field. |  | 4.4.0(24) | P1 | Model Name: iPhone 13 pro max IOS Version: 17.4 | IOS | [9 empty] | Active | Blocked | Blocked | Blocked |  |  | Android and iOS
45 | DOM-324 | Others | Emergency contact taking invalid contact number. |  | 4.4.0(24) | P1 | Model Name: iPhone 13 pro max IOS Version: 17.4 | IOS | [9 empty] | Active | Blocked | Blocked | Blocked |  |  | Android and iOS
46 | DOM-334 | MAP | Map got hangged |  | 4.4.0 (37) | P0 | Model Name: iPhone 13 pro max IOS Version: 17.4 | IOS | [10 empty] | Active | Active | Active
47 | DOM-335 | MAP | The map path is over lapping the the green path in the map |  | 4.4.0 (37) | P2 | Model Name: iPhone 13 pro max IOS Version: 17.4 | IOS | [10 empty] | Active | Active | Active
48 | DOM-336 | MAP | VG not working properly |  | 4.4.0 (37) | P1 | Model Name: iPhone 13 pro max IOS Version: 17.4 | IOS | [10 empty] | Active | Active | Active |  |  | iOS
49 | DOM-337 | MAP | Multiple simulation happening between Source and destination |  | 4.4.0 (37) | P0 | Model Name: iPhone 13 pro max IOS Version: 17.4 | IOS | [10 empty] | Active | Active | Active
50 | DOM-338 | MAP | Navigation option is get blank in map page. |  | 4.4.0 (37) | P0 | Model Name: iPhone 13 pro max IOS Version: 17.4 | IOS | [10 empty] | Active | Active | Active
51 | DOM-339 | Cluster Issue | Pressure (psi) throwing warning symbol instead of tire pressure |  | 4.4.0 (37) | P0 | Model Name: iPhone 13 pro max IOS Version: 17.4.1 | IOS | [10 empty] | Active | Active | Active
52 | https://tvsmotorcompany.atlassian.net/browse/DOM-343 | Others | Bluetooth permission allowed but not able to turn on automatically in the device. |  | 4.4.1(13) | P1 | Model Name: iPhone 12 pro max IOS Version: 17.2.1 | IOS | [11 empty] | Active | Active
53 | DOM-344 | Others | The Location permission is asking for "Always" turned on in the device. |  | 4.4.1(13) | P1 | Model Name: iPhone 12 pro max IOS Version: 17.2.1 | IOS | [11 empty] | Active | Active
54 | DOM-345 | VA | [IOS] [U490] - Nearest petrol pump and End navigation voice command is not working properly. |  | 4.5.1 (3) | P1 | Model Name: iPhone 12 pro max IOS Version: 17.2.1 | IOS | [12 empty] | Active
55 | DOM-346 | VA | [IOS] [U490] - Show my last caller throwing wrong information in the cluster. |  | 4.5.1 (3) | P1 | Model Name: iPhone 12 pro max IOS Version: 17.2.1 | IOS | [12 empty] | Active
56 | DOM-347 | VA | [IOS] [U490] - VA "Enable High speed alerts" not able to fetch these commands. |  | 4.5.1 (3) | P1 | Model Name: iPhone 12 pro max IOS Version: 17.2.1 | IOS | [12 empty] | Active
57 | DOM-348 | Others | [IOS] [U490] - Increase volume decrease volume is not working properly. |  | 4.5.1 (3) | P1 | Model Name: iPhone 12 pro max IOS Version: 17.2.1 | IOS | [12 empty] | Active
58 | DOM-351 | MAP | [IOS] [U490] - Application is getting crashed in the map screen. |  | 4.5.1 (3) | P0 | Model Name: iPhone 12 pro max IOS Version: 17.2.1 | IOS | [12 empty] | Active
59 | DOM-354 | Others | Some times Pass key is not displayed on the cluster. |  | 4.5.1 (3) | P0 | Model Name: iPhone 12 pro max IOS Version: 17.2.1 | IOS | [12 empty] | Active

## App Support team
Sl. No. | Jira Bug Id | Categories | Bug description | Reproducible in Devices | Status
1 | https://tvsmotorcompany.atlassian.net/browse/DOM-208 | Connectivity | Emergency Contact accept Invalid Mail ID | Android and iOS
2 | https://tvsmotorcompany.atlassian.net/browse/DOM-204 | Cluster Issue | Feedback section not accepting mandatory field. | Android and iOS
3 | https://tvsmotorcompany.atlassian.net/browse/DOM-207 | MAP | Shop Option is asking Registered person details | Android and iOS
4 | https://tvsmotorcompany.atlassian.net/browse/DOM-214 | Others | Warranty is same for all bike. | Android and iOS
5 | https://tvsmotorcompany.atlassian.net/browse/DOM-221 | Others | The Emergency SOS is sending SMS instead of call. | Android and iOS
6 | https://tvsmotorcompany.atlassian.net/browse/DOM-218 | Others | The Service center POI didn't showing the distance details. | Android and iOS
7 | DOM-311 | Others | Multiple spaces accepting in profile section. | iOS
8 | DOM-314 | MAP | In Last Ride Information page the map path is not forming ideal path. | iOS
9 | DOM-313 | MAP | Recentre is not woring | iOS
10 | DOM-312 | MAP | Direcction of the Navigation icon is wrongly shown in the map. | iOS
11 | DOM-321 | Others | Not able to book a Vehicle service. | Android and iOS
12 | DOM-322 | MAP | In AOG page map is not displaying. | iOS
13 | DOM-323 | Others | Feedback section able to submit without mandatory field. | Android and iOS
14 | DOM-324 | Others | Emergency contact taking invalid contact number. | Android and iOS
15 | DOM-336 | MAP | VG not working properly | iOS
16 | DOM-194 | Others | [Android][IOS]A Valid Bike image is not displayed on the home screen. | Android and iOS
17 | DOM-254 | Others | While adding the vehicle accepting mobile numbers in the place of Engine numbers. | Android and iOS
18 | DOM-255 | Others | The page redirects to the Home screen while deleting the Vehicle from the vehicle garage. | Android
19 | DOM-256 | VA | Profile image not displayed in the cluster Through the voice command "Hi buddy" | Android and iOS

## Pricol observation and status
Issue key | Summary | Android Dev Comments | Conclusion after joint testing | Status
NA | Speedo SW Version value is getting zero from cluster | Value should come properly with released version will change value should be change. | This is not implemented in cluster and not in scope for U490 | NA
DOM-292 | Need to restart the cluster once we are used to it testing continuously for 30 mins. | After taking the 30 mins ride we are not able to connect with the cluster we need to restart the cluster for BT connection. | Issue demonstrated, Cluster needs to be restarted to be discoverable by either iOS or android device. Pricol team to test and get back on their testing. | Open
DOM-291 | Digi doc upload not synching with the cluster | We analysed this issue and noticed the after sending initial frame we have received 5A 53 but not received acknowledgement frame 5A 54 (Logs & Video Attached) | Issue demonstrated, After sending 5b 4A packet, there’s a delay of 4 sec, after which 5A 53 packet is sent to resume image sync but 5A 54 ACK packet is not received in TVS connect or NRF application. Pricol team will check why 5A 54 packet is not being returned to application, (TVSM will share latest logs and video) | Open
DOM-290 | Unknown number caller calling status not displayed in the cluster. | Calling status not showing on cluster when user received call from unsaved contact (Please check screenshot from folder) | This is not implemented in cluster and not in scope for U490 | NA
DOM-289 | On-going calls are displayed as “ Calling” in the cluster. | After receive the call call status is not changing to On-going | This is not implemented in cluster and not in scope for U490 | NA
DOM-288 | Sometimes Passcode not displaying in the cluster. | We have observed this issue in random scenario we have captured video for this issue. Please check from folder. | Not able to reproduce this issue, hence closed | Closed
DOM-287 | If iOS and Android device Bluetooth settings are enabled then not detect the Cluster. | This is cluster side issue since the application has initiated the manual connection and OS has prompted for pairing however cluster is not showing the pairing code. | Issue demonstrated, TVSM team to test the mobile packet if termination packet is being sent correctly and come back on the findings (iOS app) | Open
DOM-286 | [U490]Unable to pair another device without forgetting the primary connected device. | After disconnect the Android device and then trying to connect iOS device not able to connect with cluster. | Issue demonstrated, TVSM team to test the mobile packet if termination packet is being sent correctly and come back on the findings (iOS app) | Open
DOM-285 | [U490]After pairing the cluster with an Android device, Not able to pair with the IOS device. | After disconnect the iOS device and then trying to connect Android device not able to connect with cluster. | Issue demonstrated, Pricol team will check this issue | Open
DOM-284 | [U490]For processing VA icon is not displayed. | Icon was missing on processing state, please check screenshot from folder | In CA v4.18 this is not implemented, Pricol team will provide updated software for this | Open
DOM-280 | [U490]After decline the call fuel range is not displayed and the blank space is observed in the cluster. | We analysed this issue and found few custom message not displaying on cluster. 5b 4c 00 40 4e 61 76 20 41 73 73 69 73 74 20 4f 6e 00 00 ff | In CA v4.18 this is not implemented, Pricol team will provide updated software for this | Open
DOM-279 | [U490]When we receive a missed call, In the cluster calling status is blinking. | This issue is happening when navigate is ON and user received a call then calling information is blinking. We have analysed this scenario once we get call disconnected status we stop sending the caller information to the cluster. | In CA v4.18 this is not implemented, Pricol team will come back on this issue. | Open
DOM-261 | [U490]VA is not invoking in the cluster. | From map screen if we invoke the voice assist takes time to show listening or processing state on the cluster. Logs and video attached. | In CA v4.18 this is not implemented, Pricol team will provide updated software for this | Open
DOM-256 | [U490]The Profile image is not displayed in the cluster Through the voice command "Hi buddy" | After giving the "Hey Buddy" command on cluster profile place holder is displaying but we are not received any frame from protocol sheet to send profile image data to the cluster. | This will only show default profile image. This is as per requirement | NA
DOM-306 | Not able to delete digi docs images in cluster | Some partially sync’d images in digi docs section of the cluster memory are not getting deleted. | Not able to reproduce this issue, hence closed | Closed